## Tasklist
Due Date (days) | Due Date | Status | Owner | Role | Category | Task | Comments | Report name & field
|  | Open | Computershare | Vesting | Planning | TAV election open (if applicable) & comm sent | NA
|  | Open | Computershare | Vesting | Planning | TAV election window close (if applicable) | NA
|  | Open | TA1/Computershare | TA1/Vesting | Comms | Confirm vest comm requirements (BUW comms, post vest) | TA1 confirm if CPU to send comms during vest discussions
|  | Open | Computershare | Vesting | Comms | Share template vest comms | If applicable
|  | Open | TA1 | TA1 | Comms | Approve template vest comms | If applicable
|  | Open | TA1 | TA1 | Planning | Confirm TAV setup i.e. WTC/STC/Sell All | WTC is default, TA1 to advise if this is to change | Vesting Preview & Preparation IR11: Default TAV Action
|  | Open | TA1 | TA1 | Planning | Confirm when FMV and performance will be known i.e. T-1 or T-5 | FMV date changes depending on if performance or non performance award
Vesting Date - 45 days | Thursday, 05/03/2026 | Open | TA1 |  | Planning | Raise EquateService request to initiate Vest discussions | CPES-115646
Vesting Date - 43 days | Monday, 09/03/2026 | Open | Computershare | Vesting | Planning | Review vesting population using Vesting Preview & Preparation
Vesting Date - 34 days | Friday, 20/03/2026 | Open | Computershare | Vesting | Planning | Circulate tasklist (vest timeline)
Vesting Date - 27 days | Tuesday, 31/03/2026 | Open | TA1 |  | Planning | Confirm understanding & agreement with tasks & timings
Vesting Date - 27 days | Tuesday, 31/03/2026 | Open | Computershare/TA1 | TA1/Vesting | Data | Confirm Stock Satisfactions details (contact details/ bank details)
Vesting Date - 21 days | Friday, 10/04/2026 | Open | TA1 |  | Data | Review vesting population using Vesting Preview & Preparation | Check: Employment Status, Payroll ID, Tax Rate applied, Units to Vest, Special Tax Flags & SAFE flags, FATCA & CRS status, BUW, check vesting dates and restriction periods | Vesting Preview & Preparation IR11: "Employment Status", "Payroll ID", "Tax Rate Applied" & "Tax Type Applied", "Outstanding Quantity", "Special Tax Flag", "Safe Account Identifier", "CRS FATCA Form Status"- status must be "Valid" for market transactions, "BUW" (where status is 'UNDOCUMENTED" 24% BUW will be deducted on market sales - participant to complete W8/W9 form in order to prevent BUW deduction), "Vesting Date", "Restriction Date".
Vesting Date - 21 days | Friday, 10/04/2026 | Open | TA1 |  | Data | Check Payroll Bank Accounts & SAFE account details (if applicable) |  | Company Payroll Accounts IR17 Request SAFE bank account details & verify the SAFE bank account details linked to "Safe Account Identifier" in IR11 are correct.
Vesting Date - 14 days | Tuesday, 21/04/2026 | Open | TA1 |  | Tax | Update tax rates, assign Special Tax flags & SAFE flags, update leavers |  | Vesting Preview & Preparation IR11: "Tax Rate Applied" & "Tax Type Applied", "Special Tax Flag", "Safe Account Identifier", "Employment Status"
Vesting Date - 8 days | Wednesday, 29/04/2026 | Open | TA1 |  | Data | Upload any final changes to EquatePlus & review Vesting Preview & Preparation report
Vesting Date - 7 days | Thursday, 30/04/2026 | Open | TA1 | Vesting | Data | Sign of vesting population in Vesting Preview & Preparation report | No further changes to be made once approved | Vesting Preview & Preparation IR11
Vesting Date - 7 days | Thursday, 30/04/2026 | Open | TA1 |  | Data | FMV to be confirmed | If calculation is 'closing price of day before vest' (T-1), FMV to be provided by COB on T-1, or 'T' first thing in the morning (vest date) FMV is required before CPU can run vest in UAT & confirm final units to be requested
VEST DATE
Vesting Date - 0 days | Wednesday, 13/05/2026 | Open | Computershare | Vesting | Data | Vest execution in UAT to confirm the total amount of net shares which will be requested for share transfer
Vesting Date - 0 days | Wednesday, 13/05/2026 | Open | Computershare / TA1 | Custody Team / TA1 | Stock Request | Request stock to satisfy vest event (T) | Global Custody Team to send the intruction for share transfer to Equiniti directly with TA1 in copy
VEST DATE + 1
Vesting Date + 1 days | Thursday, 14/05/2026 | Open | Computershare / TA1 | Custody Team / TA1 | Stock Satisfaction | Settlement of stock to satisfy vest event
Vesting Date + 1 days | Thursday, 14/05/2026 | Open | Computershare | Vesting | Vest Execution | Complete vest event in EquatePlus
Vesting Date + 1 days | Thursday, 14/05/2026 | Open | Computershare | Vesting | Vest Execution | Reconcile units and complete post vest checks
VEST DATE + 2
Vesting Date + 2 days | Friday, 15/05/2026 | Open | Computershare | Vesting | Event Completion | Rollover shares available in participant accounts
Vesting Date + 2 days | Friday, 15/05/2026 | Open | Computershare | Vesting | Event Completion | Any applicable restriction dates are applied to shares in SPA
Vesting Date + 2 days | Friday, 15/05/2026 | Open | TA1 |  | Data | Upload APTI file to CDI | Required in order for payroll reporting to reflect mobile tax splits | See 'Mobile Tax Processing' collateral - Tate & Lyle to advise which Admin email addresses are to receive notifications of Mobile trades placed
Vesting Date + 2 days | Friday, 15/05/2026 | Open | TA1 | TA1 | Reporting | Trade Report available |  | Trade Report
VEST DATE + 3
Vesting Date + 3 days | Monday, 18/05/2026 | Open | TA1 | TA1 | Payroll Reporting | Payroll reporting available with any applicable FX rates on T+3 | FX not applicable for WTC

## Sheet1 (hidden)
Add to powerpoint
SAFE check population in pre vest check & bank account details check report and update alloc file to insert safe flag
Key fields in the pre vest report under other tab
Align with client:
Award: Jul, Nov, Dec - check potentially quarterly
Vest dates upcoming - RSA 01 April vest & PSP- 30 Jan (5 ppl) & 30 June
Options all vested, for 2 ppl, with tax rates, no STF, no China Safe
Div: Jan & August
No div equivalents -- default is DRIP, participants can elect Cash
Default transaction - WTC or hold all (depending on tax status)
China SAFE & Special tax required
Group Bonus Plan performance measured prior to award being granted in EquatePlus
PSPs - x4 performance measures applied at vest, performance is over 3 years from grant (cliff vest)
Do vest setups check, proceeds (none cos wtc), SAFE account& ceo/cfo 2 year restriction & whole shares vesting? Div default is DRIP, participants can elect Cash, STF setups correct i.e. external cash handling setup ok? Client to check bank acocutns including SAFE
Add in performance application for PSP - when is this applied?
1 ppt with outstanding performance to be applied?
Vest shares sourced from EBT (equiniti)
1. Playback and align on vesting setups/ expectations
2. go trhough timeline & tasks - icluding interpreting pre vest report checks (list)
3. post vest - special tax handling
share collateral with this in mind & updated tiemline based on client input